## departments
Department_ID | Department_Name | Department_Head | Employee_Count
D001 | Human Resources | VP Human Resources | 95
D002 | Operations | VP Operations | 620
D003 | Supply Chain | Director Supply Chain | 180
D004 | Finance | CFO | 130
D005 | Customer Service | Director Customer Experience | 260
D006 | Information Technology | CIO | 170
D007 | Quality Assurance | Director Quality | 145
D008 | Sales & Marketing | CMO | 250
D009 | Engineering | VP Engineering | 150

## ai_systems
AI_System_ID | System_Name | Department_ID | AI_Type | Purpose | Vendor_Type | Deployment_Type | Data_Sensitivity | Decision_Impact | Human_Decision_Involved | System_Status | System_Owner | Deployment_Date | Last_Review_Date
AI001 | Resume Screening Assistant | D001 | Machine Learning | Prioritize job applicants | Third-Party | Cloud | High | High | Yes | Active | Talent Acquisition Manager | 2024-03-15 | 2026-06-12
AI002 | Employee Scheduling Optimizer | D001 | Optimization AI | Recommend employee work schedules | Internal | Cloud | Moderate | Medium | Yes | Active | HR Operations Manager | 2024-03-16 | 2026-06-13
AI003 | Predictive Maintenance System | D002 | Predictive ML | Predict equipment failures | Third-Party | Hybrid | Moderate | High | Yes | Active | Maintenance Manager | 2024-03-17 | 2026-06-14
AI004 | Production Scheduling Optimizer | D002 | Optimization AI | Optimize production schedules | Internal | On-Premises | Moderate | High | Yes | Active | Production Planning Manager | 2024-03-18 | 2026-06-15
AI005 | Visual Defect Detection | D007 | Computer Vision | Identify defective products | Third-Party | On-Premises | Low | High | Yes | Active | Quality Manager | 2024-03-19 | 2026-06-16
AI006 | Demand Forecasting Model | D003 | Predictive ML | Forecast product demand | Internal | Cloud | Moderate | Medium | Yes | Active | Demand Planning Manager | 2024-03-20 | 2026-06-17
AI007 | Supplier Risk Predictor | D003 | Machine Learning | Predict supplier disruption risk | Third-Party | Cloud | Moderate | High | Yes | Active | Supplier Risk Manager | 2024-03-21 | 2026-06-18
AI008 | Invoice Fraud Detection | D004 | Anomaly Detection | Identify suspicious invoices | Third-Party | Cloud | High | High | Yes | Active | Finance Controls Manager | 2024-03-22 | 2026-06-19
AI009 | Customer Support Chatbot | D005 | Generative AI | Answer customer questions | Third-Party | Cloud | High | Medium | Partial | Active | Customer Experience Manager | 2024-03-23 | 2026-06-20
AI010 | Internal Knowledge Assistant | D006 | Generative AI | Answer employee questions | Third-Party | Cloud | Restricted | Medium | Partial | Active | IT Applications Manager | 2024-03-24 | 2026-06-21
AI011 | Customer Sentiment Analyzer | D005 | Natural Language Processing | Analyze customer feedback and sentiment | Third-Party | Cloud | Moderate | Medium | Yes | Active | Customer Insights Manager | 2024-03-25 | 2026-06-22
AI012 | Customer Churn Predictor | D005 | Predictive ML | Predict customers likely to stop purchasing | Internal | Cloud | Moderate | Medium | Yes | Active | Customer Experience Manager | 2024-03-26 | 2026-06-23
AI013 | IT Security Anomaly Detector | D006 | Anomaly Detection | Detect unusual network and account activity | Third-Party | Hybrid | Restricted | High | Yes | Active | Cybersecurity Manager | 2024-03-27 | 2026-06-24
AI014 | Automated Help Desk Assistant | D006 | Generative AI | Assist employees with routine IT support | Third-Party | Cloud | High | Medium | Partial | Active | IT Service Manager | 2024-03-28 | 2026-06-25
AI015 | Access Risk Analyzer | D006 | Machine Learning | Identify potentially excessive user access privileges | Internal | On-Premises | Restricted | High | Yes | Active | Identity and Access Manager | 2024-03-29 | 2026-06-26
AI016 | Warranty Claim Analyzer | D007 | Machine Learning | Identify unusual product warranty claims | Internal | Cloud | Moderate | Medium | Yes | Active | Quality Systems Manager | 2024-03-30 | 2026-06-27
AI017 | Quality Trend Predictor | D007 | Predictive ML | Predict future manufacturing quality issues | Internal | On-Premises | Moderate | High | Yes | Active | Quality Engineering Manager | 2024-03-31 | 2026-06-28
AI018 | Root Cause Recommendation Tool | D007 | Generative AI | Suggest possible causes of recurring quality defects | Internal | Hybrid | Moderate | High | Yes | Active | Continuous Improvement Manager | 2024-04-01 | 2026-06-29
AI019 | Marketing Content Generator | D008 | Generative AI | Generate first drafts of marketing content | Third-Party | Cloud | Moderate | Low | Yes | Active | Digital Marketing Manager | 2024-04-02 | 2026-06-30
AI020 | Customer Segmentation Model | D008 | Machine Learning | Group customers based on purchasing behaviour | Internal | Cloud | High | Medium | Yes | Active | Marketing Analytics Manager | 2024-04-03 | 2026-07-01
AI021 | Product Recommendation Engine | D008 | Recommendation System | Recommend products to customers | Third-Party | Cloud | High | Medium | Partial | Active | E-Commerce Manager | 2024-04-04 | 2026-07-02
AI022 | Dynamic Pricing Assistant | D008 | Optimization AI | Recommend product pricing adjustments | Internal | Cloud | Moderate | High | Yes | Active | Pricing Manager | 2024-04-05 | 2026-07-03
AI023 | Engineering Design Assistant | D009 | Generative AI | Assist engineers with design concepts and documentation | Third-Party | Cloud | Restricted | High | Yes | Active | Engineering Design Manager | 2024-04-06 | 2026-07-04
AI024 | Equipment Performance Simulator | D009 | Predictive ML | Predict equipment performance under operating conditions | Internal | On-Premises | Moderate | High | Yes | Active | Systems Engineering Manager | 2024-04-07 | 2026-07-05
AI025 | Automated Drawing Review | D009 | Computer Vision | Identify potential issues in technical drawings | Internal | On-Premises | Restricted | High | Yes | Active | Engineering Quality Manager | 2024-04-08 | 2026-07-06
AI026 | Energy Consumption Optimizer | D002 | Optimization AI | Recommend production settings to reduce energy use | Internal | On-Premises | Low | Medium | Yes | Active | Plant Operations Manager | 2024-04-09 | 2026-07-07
AI027 | Safety Incident Predictor | D002 | Predictive ML | Predict operating conditions associated with workplace incidents | Internal | Hybrid | High | High | Yes | Active | EHS Manager | 2024-04-10 | 2026-07-08
AI028 | Transportation Route Optimizer | D003 | Optimization AI | Optimize material transportation and delivery routes | Third-Party | Cloud | Moderate | Medium | Yes | Active | Logistics Manager | 2024-04-11 | 2026-07-09
AI029 | Inventory Replenishment Model | D003 | Predictive ML | Recommend inventory replenishment quantities and timing | Internal | Cloud | Moderate | Medium | Yes | Active | Inventory Planning Manager | 2024-04-12 | 2026-07-10
AI030 | Supplier Contract Analyzer | D003 | Generative AI | Review supplier contracts and highlight potential risks | Third-Party | Cloud | Restricted | High | Yes | Active | Strategic Sourcing Manager | 2024-04-13 | 2026-07-11
AI031 | Cash Flow Forecasting Model | D004 | Predictive ML | Forecast short-term organizational cash flow | Internal | Cloud | High | High | Yes | Active | Treasury Manager | 2024-04-14 | 2026-07-12
AI032 | Expense Audit Assistant | D004 | Anomaly Detection | Identify unusual employee expenses for review | Third-Party | Cloud | High | Medium | Yes | Active | Internal Controls Manager | 2024-04-15 | 2026-07-13
AI033 | Customer Credit Risk Model | D004 | Machine Learning | Assess customer payment and credit risk | Internal | On-Premises | High | High | Yes | Active | Credit Manager | 2024-04-16 | 2026-07-14
AI034 | Call Summarization Assistant | D005 | Generative AI | Summarize customer service conversations | Third-Party | Cloud | High | Medium | Yes | Active | Contact Centre Manager | 2024-04-17 | 2026-07-15
AI035 | Complaint Routing Model | D005 | Natural Language Processing | Categorize and route customer complaints | Internal | Cloud | Moderate | Medium | Partial | Active | Customer Service Operations Manager | 2024-04-18 | 2026-07-16
AI036 | Software Development Assistant | D006 | Generative AI | Assist developers with code generation and documentation | Third-Party | Cloud | Restricted | High | Yes | Active | Software Engineering Manager | 2024-04-19 | 2026-07-17
AI037 | Phishing Detection System | D006 | Machine Learning | Identify potentially malicious email messages | Third-Party | Cloud | Restricted | High | Partial | Active | Cybersecurity Operations Manager | 2024-04-20 | 2026-07-18
AI038 | Sensitive Data Classifier | D006 | Natural Language Processing | Detect and classify sensitive information in company files | Internal | Hybrid | Restricted | High | Yes | Active | Data Security Manager | 2024-04-21 | 2026-07-19
AI039 | Calibration Drift Predictor | D007 | Predictive ML | Predict when production measurement equipment requires calibration | Internal | On-Premises | Moderate | High | Yes | Active | Quality Engineering Manager | 2024-04-22 | 2026-07-20
AI040 | Supplier Quality Risk Model | D007 | Machine Learning | Predict suppliers at risk of recurring quality issues | Internal | Cloud | Moderate | High | Yes | Active | Supplier Quality Manager | 2024-04-23 | 2026-07-21
AI041 | Campaign Performance Predictor | D008 | Predictive ML | Forecast marketing campaign performance | Third-Party | Cloud | Moderate | Low | Yes | Active | Marketing Analytics Manager | 2024-04-24 | 2026-07-22
AI042 | Sales Lead Scoring Model | D008 | Machine Learning | Prioritize sales leads based on likelihood of conversion | Internal | Cloud | High | Medium | Yes | Active | Sales Operations Manager | 2024-04-25 | 2026-07-23
AI043 | Social Media Monitoring Assistant | D008 | Natural Language Processing | Analyze public social media discussions about company products | Third-Party | Cloud | Low | Low | Partial | Active | Brand Manager | 2024-04-26 | 2026-07-24
AI044 | Digital Twin Optimization System | D009 | Optimization AI | Simulate and optimize manufacturing system performance | Internal | On-Premises | Moderate | High | Yes | Active | Systems Engineering Manager | 2024-04-27 | 2026-07-25
AI045 | Engineering Requirements Assistant | D009 | Generative AI | Summarize and analyze technical requirements for engineering projects | Third-Party | Cloud | Restricted | High | Yes | Active | Engineering Program Manager | 2024-04-28 | 2026-07-26
AI046 | Employee Attrition Predictor | D001 | Predictive ML | Identify employees with elevated likelihood of leaving the organization | Internal | Cloud | High | High | Yes | Active | People Analytics Manager | 2024-04-29 | 2026-07-27
AI047 | Employee Learning Recommender | D001 | Recommendation System | Recommend training content based on employee roles and skills | Third-Party | Cloud | High | Medium | Partial | Active | Learning and Development Manager | 2024-04-30 | 2026-07-28
AI048 | Warehouse Robotics Routing System | D002 | Optimization AI | Optimize movement routes for automated warehouse equipment | Third-Party | On-Premises | Low | High | Partial | Active | Warehouse Operations Manager | 2024-05-01 | 2026-07-29
AI049 | Workplace Safety Vision System | D002 | Computer Vision | Detect unsafe conditions and missing protective equipment | Third-Party | On-Premises | High | High | Yes | Pilot | EHS Manager | 2024-05-02 | 2026-07-30
AI050 | Financial Close Assistant | D004 | Generative AI | Assist finance staff with account reconciliation and close documentation | Third-Party | Cloud | Restricted | High | Yes | Pilot | Financial Reporting Manager | 2024-05-03 | 2026-07-31

## risk_assessments
Assessment_ID | AI_System_ID | Privacy_Risk | Fairness_Risk | Security_Risk | Reliability_Risk | Transparency_Risk | Human_Oversight_Risk | Overall_Risk_Score | Risk_Level | Assessment_Date | Reviewer
RA001 | AI001 | 4 | 5 | 3 | 4 | 5 | 4 | 4.2 | Critical | 2026-09-20 | AI Governance Analyst
RA002 | AI002 | 4 | 4 | 3 | 3 | 3 | 3 | 3.4 | High | 2026-09-20 | AI Governance Analyst
RA003 | AI003 | 2 | 1 | 4 | 5 | 3 | 3 | 2.85 | Moderate | 2026-09-20 | AI Governance Analyst
RA004 | AI004 | 2 | 1 | 3 | 4 | 3 | 3 | 2.55 | Moderate | 2026-09-20 | AI Governance Analyst
RA005 | AI005 | 1 | 1 | 3 | 5 | 3 | 3 | 2.5 | Moderate | 2026-09-20 | AI Governance Analyst
RA006 | AI006 | 2 | 1 | 3 | 4 | 3 | 3 | 2.55 | Moderate | 2026-09-20 | AI Governance Analyst
RA007 | AI007 | 2 | 2 | 3 | 4 | 4 | 3 | 2.9 | Moderate | 2026-09-20 | AI Governance Analyst
RA008 | AI008 | 4 | 3 | 5 | 4 | 4 | 4 | 3.95 | High | 2026-09-20 | AI Governance Analyst
RA009 | AI009 | 4 | 3 | 4 | 4 | 5 | 4 | 3.95 | High | 2026-09-20 | AI Governance Analyst
RA010 | AI010 | 5 | 2 | 5 | 4 | 5 | 4 | 4.1 | Critical | 2026-09-20 | AI Governance Analyst
RA011 | AI011 | 3 | 3 | 3 | 2 | 3 | 2 | 2.7 | Moderate | 2026-09-20 | AI Governance Analyst
RA012 | AI012 | 4 | 3 | 3 | 3 | 3 | 3 | 3.2 | High | 2026-09-20 | AI Governance Analyst
RA013 | AI013 | 5 | 1 | 5 | 5 | 4 | 3 | 3.75 | High | 2026-09-20 | AI Governance Analyst
RA014 | AI014 | 4 | 2 | 4 | 3 | 5 | 4 | 3.6 | High | 2026-09-20 | AI Governance Analyst
RA015 | AI015 | 5 | 3 | 5 | 4 | 4 | 4 | 4.15 | Critical | 2026-09-20 | AI Governance Analyst
RA016 | AI016 | 3 | 2 | 3 | 3 | 3 | 3 | 2.8 | Moderate | 2026-09-20 | AI Governance Analyst
RA017 | AI017 | 2 | 1 | 3 | 5 | 3 | 3 | 2.7 | Moderate | 2026-09-20 | AI Governance Analyst
RA018 | AI018 | 2 | 1 | 3 | 4 | 5 | 4 | 3 | High | 2026-09-20 | AI Governance Analyst
RA019 | AI019 | 2 | 2 | 2 | 2 | 4 | 2 | 2.3 | Moderate | 2026-09-20 | AI Governance Analyst
RA020 | AI020 | 4 | 4 | 3 | 3 | 4 | 3 | 3.55 | High | 2026-09-20 | AI Governance Analyst
RA021 | AI021 | 4 | 3 | 3 | 3 | 4 | 4 | 3.5 | High | 2026-09-20 | AI Governance Analyst
RA022 | AI022 | 2 | 4 | 3 | 4 | 4 | 4 | 3.45 | High | 2026-09-20 | AI Governance Analyst
RA023 | AI023 | 5 | 1 | 5 | 4 | 5 | 3 | 3.75 | High | 2026-09-20 | AI Governance Analyst
RA024 | AI024 | 2 | 1 | 4 | 5 | 3 | 3 | 2.85 | Moderate | 2026-09-20 | AI Governance Analyst
RA025 | AI025 | 4 | 1 | 5 | 5 | 3 | 3 | 3.4 | High | 2026-09-20 | AI Governance Analyst
RA026 | AI026 | 1 | 1 | 2 | 3 | 2 | 2 | 1.75 | Low | 2026-09-20 | AI Governance Analyst
RA027 | AI027 | 4 | 3 | 4 | 5 | 4 | 4 | 3.95 | High | 2026-09-20 | AI Governance Analyst
RA028 | AI028 | 2 | 1 | 3 | 3 | 3 | 2 | 2.25 | Moderate | 2026-09-20 | AI Governance Analyst
RA029 | AI029 | 2 | 1 | 3 | 3 | 3 | 2 | 2.25 | Moderate | 2026-09-20 | AI Governance Analyst
RA030 | AI030 | 4 | 2 | 5 | 4 | 5 | 4 | 3.9 | High | 2026-09-20 | AI Governance Analyst
RA031 | AI031 | 4 | 1 | 5 | 4 | 4 | 3 | 3.4 | High | 2026-09-20 | AI Governance Analyst
RA032 | AI032 | 4 | 3 | 4 | 3 | 4 | 3 | 3.5 | High | 2026-09-20 | AI Governance Analyst
RA033 | AI033 | 4 | 5 | 5 | 4 | 5 | 4 | 4.5 | Critical | 2026-09-20 | AI Governance Analyst
RA034 | AI034 | 4 | 2 | 4 | 3 | 4 | 3 | 3.3 | High | 2026-09-20 | AI Governance Analyst
RA035 | AI035 | 3 | 3 | 3 | 3 | 3 | 4 | 3.15 | High | 2026-09-20 | AI Governance Analyst
RA036 | AI036 | 5 | 1 | 5 | 4 | 5 | 4 | 3.9 | High | 2026-09-20 | AI Governance Analyst
RA037 | AI037 | 4 | 1 | 5 | 5 | 4 | 4 | 3.7 | High | 2026-09-20 | AI Governance Analyst
RA038 | AI038 | 5 | 2 | 5 | 5 | 4 | 3 | 3.95 | High | 2026-09-20 | AI Governance Analyst
RA039 | AI039 | 2 | 1 | 3 | 5 | 3 | 3 | 2.7 | Moderate | 2026-09-20 | AI Governance Analyst
RA040 | AI040 | 2 | 2 | 3 | 4 | 4 | 3 | 2.9 | Moderate | 2026-09-20 | AI Governance Analyst
RA041 | AI041 | 2 | 1 | 2 | 2 | 3 | 2 | 1.95 | Low | 2026-09-20 | AI Governance Analyst
RA042 | AI042 | 4 | 3 | 3 | 3 | 4 | 3 | 3.35 | High | 2026-09-20 | AI Governance Analyst
RA043 | AI043 | 1 | 2 | 2 | 2 | 3 | 3 | 2.1 | Moderate | 2026-09-20 | AI Governance Analyst
RA044 | AI044 | 2 | 1 | 4 | 5 | 3 | 3 | 2.85 | Moderate | 2026-09-20 | AI Governance Analyst
RA045 | AI045 | 5 | 1 | 5 | 4 | 5 | 3 | 3.75 | High | 2026-09-20 | AI Governance Analyst
RA046 | AI046 | 5 | 5 | 4 | 4 | 5 | 4 | 4.55 | Critical | 2026-09-20 | AI Governance Analyst
RA047 | AI047 | 4 | 4 | 3 | 3 | 4 | 4 | 3.7 | High | 2026-09-20 | AI Governance Analyst
RA048 | AI048 | 1 | 1 | 4 | 5 | 3 | 4 | 2.8 | Moderate | 2026-09-20 | AI Governance Analyst
RA049 | AI049 | 4 | 2 | 4 | 5 | 3 | 4 | 3.6 | High | 2026-09-20 | AI Governance Analyst
RA050 | AI050 | 5 | 1 | 5 | 4 | 5 | 4 | 3.9 | High | 2026-09-20 | AI Governance Analyst

## governance_controls
Control_ID | AI_System_ID | Control_Category | Control_Name | Control_Status | Control_Effectiveness | Control_Owner | Implementation_Date | Last_Test_Date | Next_Review_Date
C001 | AI001 | Human Oversight | Mandatory recruiter review of AI recommendations | Implemented | Effective | Talent Acquisition Manager | 2024-03-15 | 2026-06-12 | 2026-12-12
C002 | AI001 | Fairness | Quarterly bias and selection-rate testing | Partial | Partially Effective | People Analytics Manager | 2025-01-10 | 2026-06-12 | 2026-09-30
C003 | AI001 | Transparency | Documented explanation for candidate recommendations | Missing | Not Effective | Talent Acquisition Manager |  |  | 2026-10-15
C004 | AI002 | Human Oversight | Manager approval required before schedules are published | Implemented | Effective | HR Operations Manager | 2024-09-01 | 2026-05-20 | 2026-11-20
C005 | AI002 | Fairness | Schedule fairness review across employee groups | Partial | Partially Effective | HR Operations Manager | 2025-02-14 | 2026-05-20 | 2026-11-20
C006 | AI002 | Monitoring | Monthly review of scheduling overrides and complaints | Implemented | Effective | HR Operations Manager | 2024-10-01 | 2026-08-01 | 2026-09-30
C007 | AI003 | Reliability | Monthly predictive accuracy review | Implemented | Effective | Maintenance Manager | 2023-06-10 | 2026-07-18 | 2026-10-18
C008 | AI003 | Human Oversight | Maintenance technician validates failure alerts | Implemented | Effective | Maintenance Manager | 2023-06-10 | 2026-07-18 | 2026-10-18
C009 | AI003 | Monitoring | Model drift monitoring for equipment sensor data | Partial | Partially Effective | Reliability Engineer | 2025-03-01 | 2026-07-18 | 2026-10-18
C010 | AI004 | Human Oversight | Production planner approval of optimized schedules | Implemented | Effective | Production Planning Manager | 2023-11-05 | 2026-04-22 | 2026-10-22
C011 | AI004 | Reliability | Production schedule performance review | Implemented | Effective | Production Planning Manager | 2024-01-15 | 2026-07-15 | 2026-10-15
C012 | AI004 | Monitoring | Monitor schedule deviations and manual overrides | Implemented | Effective | Operations Analytics Manager | 2024-02-01 | 2026-08-01 | 2026-11-01
C013 | AI005 | Reliability | Routine defect-detection accuracy validation | Implemented | Effective | Quality Manager | 2024-01-18 | 2026-08-05 | 2026-11-05
C014 | AI005 | Human Oversight | Quality inspector reviews rejected products | Implemented | Effective | Quality Manager | 2024-01-18 | 2026-08-05 | 2026-11-05
C015 | AI005 | Monitoring | False-positive and false-negative tracking | Implemented | Effective | Quality Engineering Manager | 2024-03-10 | 2026-08-05 | 2026-11-05
C016 | AI006 | Reliability | Monthly forecast accuracy review | Implemented | Effective | Demand Planning Manager | 2023-08-21 | 2026-05-11 | 2026-11-11
C017 | AI006 | Human Oversight | Planner approval required for major forecast changes | Implemented | Effective | Demand Planning Manager | 2023-08-21 | 2026-05-11 | 2026-11-11
C018 | AI006 | Monitoring | Monitor forecast error by product category | Implemented | Effective | Supply Chain Analytics Manager | 2024-01-08 | 2026-08-10 | 2026-11-10
C019 | AI007 | Reliability | Quarterly supplier-risk model validation | Implemented | Effective | Supplier Risk Manager | 2024-05-09 | 2026-07-01 | 2026-10-01
C020 | AI007 | Human Oversight | Supplier manager validates high-risk alerts | Implemented | Effective | Supplier Risk Manager | 2024-05-09 | 2026-07-01 | 2026-10-01
C021 | AI007 | Transparency | Document key factors influencing supplier risk scores | Partial | Partially Effective | Supplier Risk Manager | 2025-02-12 | 2026-07-01 | 2026-10-01
C022 | AI008 | Security | Restricted access to fraud-detection data and results | Implemented | Effective | Finance Controls Manager | 2023-10-30 | 2026-06-28 | 2026-12-28
C023 | AI008 | Human Oversight | Finance investigator reviews flagged invoices | Implemented | Effective | Finance Controls Manager | 2023-10-30 | 2026-06-28 | 2026-12-28
C024 | AI008 | Monitoring | Monthly false-positive fraud alert analysis | Partial | Partially Effective | Internal Controls Manager | 2024-06-01 | 2026-06-28 | 2026-09-28
C025 | AI009 | Security | Prompt and input filtering for sensitive data | Implemented | Effective | Customer Experience Manager | 2025-02-14 | 2026-08-15 | 2026-11-15
C026 | AI009 | Human Oversight | Escalation to human agent for complex requests | Implemented | Effective | Customer Experience Manager | 2025-02-14 | 2026-08-15 | 2026-11-15
C027 | AI009 | Monitoring | Hallucination and incorrect-answer monitoring | Partial | Partially Effective | Customer Experience Manager | 2025-05-01 | 2026-08-15 | 2026-10-15
C028 | AI010 | Security | Role-based access to internal knowledge sources | Implemented | Effective | IT Applications Manager | 2025-06-02 | 2026-08-21 | 2026-11-21
C029 | AI010 | Privacy | Prevent restricted information from appearing in unauthorized responses | Partial | Partially Effective | Data Security Manager | 2025-07-15 | 2026-08-21 | 2026-10-21
C030 | AI010 | Monitoring | Regular review of generated answers for hallucinations | Missing | Not Effective | IT Applications Manager |  |  | 2026-10-01
C031 | AI011 | Monitoring | Monthly customer sentiment model performance review | Implemented | Effective | Customer Insights Manager | 2024-07-12 | 2026-06-30 | 2026-09-30
C032 | AI011 | Privacy | Removal of unnecessary personal identifiers from feedback data | Implemented | Effective | Data Privacy Manager | 2024-08-01 | 2026-06-30 | 2026-12-30
C033 | AI011 | Reliability | Manual review of low-confidence sentiment classifications | Partial | Partially Effective | Customer Insights Manager | 2025-01-15 | 2026-06-30 | 2026-09-30
C034 | AI012 | Monitoring | Quarterly churn model accuracy review | Implemented | Effective | Customer Experience Manager | 2024-02-20 | 2026-05-16 | 2026-11-16
C035 | AI012 | Human Oversight | Retention team reviews high-risk customer predictions | Implemented | Effective | Customer Experience Manager | 2024-02-20 | 2026-05-16 | 2026-11-16
C036 | AI012 | Fairness | Review churn predictions for unequal treatment across customer groups | Partial | Partially Effective | Customer Analytics Manager | 2025-03-01 | 2026-05-16 | 2026-11-16
C037 | AI013 | Security | Continuous monitoring of suspicious network activity | Implemented | Effective | Cybersecurity Manager | 2023-09-15 | 2026-07-25 | 2026-10-25
C038 | AI013 | Human Oversight | Security analyst validates high-severity alerts | Implemented | Effective | Cybersecurity Operations Manager | 2023-09-15 | 2026-07-25 | 2026-10-25
C039 | AI013 | Monitoring | Regular false-positive and false-negative review | Implemented | Effective | Cybersecurity Manager | 2024-01-10 | 2026-07-25 | 2026-10-25
C040 | AI014 | Security | Prevent sensitive company data from being exposed in generated responses | Partial | Partially Effective | IT Service Manager | 2025-03-10 | 2026-08-08 | 2026-10-08
C041 | AI014 | Human Oversight | Escalate unresolved requests to human IT staff | Implemented | Effective | IT Service Manager | 2025-03-10 | 2026-08-08 | 2026-11-08
C042 | AI014 | Monitoring | Review incorrect or misleading help desk responses | Partial | Partially Effective | IT Service Manager | 2025-06-01 | 2026-08-08 | 2026-10-08
C043 | AI015 | Security | Restricted administrator access to identity and access data | Implemented | Effective | Identity and Access Manager | 2024-04-22 | 2026-06-19 | 2026-12-19
C044 | AI015 | Human Oversight | Security analyst reviews all high-risk access findings | Implemented | Effective | Identity and Access Manager | 2024-04-22 | 2026-06-19 | 2026-12-19
C045 | AI015 | Monitoring | Quarterly validation of access risk scoring rules | Partial | Partially Effective | Cybersecurity Governance Manager | 2025-01-20 | 2026-06-19 | 2026-09-19
C046 | AI016 | Human Oversight | Quality team reviews claims flagged as unusual | Implemented | Effective | Quality Systems Manager | 2024-06-17 | 2026-04-28 | 2026-10-28
C047 | AI016 | Monitoring | Monitor claim detection false-positive rate | Implemented | Effective | Quality Systems Manager | 2024-09-01 | 2026-07-01 | 2026-10-01
C048 | AI016 | Transparency | Document primary factors used to flag warranty claims | Partial | Partially Effective | Quality Systems Manager | 2025-02-10 | 2026-04-28 | 2026-10-28
C049 | AI017 | Reliability | Quarterly quality prediction accuracy review | Implemented | Effective | Quality Engineering Manager | 2023-12-05 | 2026-07-14 | 2026-10-14
C050 | AI017 | Human Oversight | Quality engineer validates critical quality-risk predictions | Implemented | Effective | Quality Engineering Manager | 2023-12-05 | 2026-07-14 | 2026-10-14
C051 | AI017 | Monitoring | Production data drift monitoring | Implemented | Effective | Quality Analytics Manager | 2024-05-01 | 2026-07-14 | 2026-10-14
C052 | AI018 | Human Oversight | Engineer validates AI-generated root-cause recommendations | Implemented | Effective | Continuous Improvement Manager | 2025-01-21 | 2026-08-02 | 2026-11-02
C053 | AI018 | Transparency | Require supporting evidence for suggested root causes | Partial | Partially Effective | Continuous Improvement Manager | 2025-03-01 | 2026-08-02 | 2026-10-02
C054 | AI018 | Monitoring | Review incorrect root-cause recommendations | Partial | Partially Effective | Quality Engineering Manager | 2025-04-15 | 2026-08-02 | 2026-10-02
C055 | AI019 | Human Oversight | Marketing staff review all AI-generated content before publication | Implemented | Effective | Digital Marketing Manager | 2025-04-03 | 2026-08-12 | 2026-11-12
C056 | AI019 | Transparency | Require disclosure of AI-assisted content creation internally | Implemented | Effective | Digital Marketing Manager | 2025-04-03 | 2026-08-12 | 2026-11-12
C057 | AI019 | Monitoring | Quarterly review of inaccurate or inappropriate generated content | Implemented | Effective | Brand Manager | 2025-05-15 | 2026-08-12 | 2026-11-12
C058 | AI020 | Privacy | Limit customer data used for segmentation to approved fields | Implemented | Effective | Marketing Analytics Manager | 2023-07-24 | 2026-05-29 | 2026-11-29
C059 | AI020 | Fairness | Review customer segments for inappropriate demographic proxies | Partial | Partially Effective | Marketing Analytics Manager | 2024-05-10 | 2026-05-29 | 2026-11-29
C060 | AI020 | Human Oversight | Marketing analyst validates segments before campaign use | Implemented | Effective | Marketing Analytics Manager | 2023-07-24 | 2026-05-29 | 2026-11-29
C061 | AI021 | Privacy | Restrict customer-profile attributes used for recommendations | Implemented | Effective | E-Commerce Manager | 2024-08-08 | 2026-07-07 | 2027-01-07
C062 | AI021 | Fairness | Monitor recommendation exposure across customer groups | Missing | Not Effective | E-Commerce Manager |  |  | 2026-10-30
C063 | AI021 | Monitoring | Track recommendation click-through and complaint rates | Implemented | Effective | E-Commerce Manager | 2024-09-01 | 2026-07-07 | 2026-10-07
C064 | AI022 | Human Oversight | Pricing manager approval required for major price changes | Implemented | Effective | Pricing Manager | 2024-11-18 | 2026-06-05 | 2026-12-05
C065 | AI022 | Fairness | Review pricing recommendations for discriminatory or unfair outcomes | Partial | Partially Effective | Pricing Manager | 2025-02-01 | 2026-06-05 | 2026-09-05
C066 | AI022 | Monitoring | Track manual pricing overrides and customer complaints | Implemented | Effective | Pricing Manager | 2024-12-01 | 2026-08-01 | 2026-11-01
C067 | AI023 | Security | Restrict AI assistant access to approved engineering repositories | Implemented | Effective | Engineering Design Manager | 2025-05-12 | 2026-08-18 | 2026-11-18
C068 | AI023 | Human Oversight | Engineer approval required before AI-generated designs are used | Implemented | Effective | Engineering Design Manager | 2025-05-12 | 2026-08-18 | 2026-11-18
C069 | AI023 | Monitoring | Review AI-generated design errors and unsafe suggestions | Partial | Partially Effective | Engineering Quality Manager | 2025-07-01 | 2026-08-18 | 2026-10-18
C070 | AI024 | Reliability | Validate simulation predictions against physical test results | Implemented | Effective | Systems Engineering Manager | 2023-05-26 | 2026-06-24 | 2026-12-24
C071 | AI024 | Human Oversight | Engineer approval required for simulation-based design decisions | Implemented | Effective | Systems Engineering Manager | 2023-05-26 | 2026-06-24 | 2026-12-24
C072 | AI024 | Monitoring | Track model prediction errors under changing operating conditions | Implemented | Effective | Systems Engineering Manager | 2024-01-15 | 2026-06-24 | 2026-09-24
C073 | AI025 | Security | Restrict access to confidential engineering drawings | Implemented | Effective | Engineering Quality Manager | 2024-03-04 | 2026-07-20 | 2027-01-20
C074 | AI025 | Human Oversight | Engineer manually verifies all identified drawing issues | Implemented | Effective | Engineering Quality Manager | 2024-03-04 | 2026-07-20 | 2027-01-20
C075 | AI025 | Reliability | Quarterly review of missed and incorrectly flagged drawing defects | Partial | Partially Effective | Engineering Quality Manager | 2024-10-01 | 2026-07-20 | 2026-10-20
C076 | AI026 | Reliability | Monthly review of energy optimization performance | Implemented | Effective | Plant Operations Manager | 2024-02-11 | 2026-06-16 | 2026-12-16
C077 | AI026 | Human Oversight | Operations staff approve major equipment setting changes | Implemented | Effective | Plant Operations Manager | 2024-02-11 | 2026-06-16 | 2026-12-16
C078 | AI026 | Monitoring | Track energy savings and production-performance tradeoffs | Implemented | Effective | Operations Analytics Manager | 2024-05-01 | 2026-08-01 | 2026-11-01
C079 | AI027 | Reliability | Quarterly validation of workplace incident predictions | Implemented | Effective | EHS Manager | 2024-10-07 | 2026-07-30 | 2026-10-30
C080 | AI027 | Human Oversight | Safety professional reviews all high-risk alerts | Implemented | Effective | EHS Manager | 2024-10-07 | 2026-07-30 | 2026-10-30
C081 | AI027 | Monitoring | Track missed incidents and false-positive safety alerts | Partial | Partially Effective | EHS Manager | 2025-02-01 | 2026-07-30 | 2026-10-30
C082 | AI028 | Reliability | Monthly route optimization performance review | Implemented | Effective | Logistics Manager | 2023-04-19 | 2026-05-08 | 2026-11-08
C083 | AI028 | Human Oversight | Dispatcher approval required for major route changes | Implemented | Effective | Logistics Manager | 2023-04-19 | 2026-05-08 | 2026-11-08
C084 | AI028 | Monitoring | Track route deviations delivery delays and manual overrides | Implemented | Effective | Transportation Manager | 2024-01-15 | 2026-08-05 | 2026-11-05
C085 | AI029 | Reliability | Monthly replenishment forecast accuracy review | Implemented | Effective | Inventory Planning Manager | 2023-09-11 | 2026-06-03 | 2026-12-03
C086 | AI029 | Human Oversight | Planner approval required for unusual replenishment recommendations | Implemented | Effective | Inventory Planning Manager | 2023-09-11 | 2026-06-03 | 2026-12-03
C087 | AI029 | Monitoring | Monitor stockouts excess inventory and recommendation overrides | Implemented | Effective | Inventory Planning Manager | 2024-02-01 | 2026-08-03 | 2026-11-03
C088 | AI030 | Security | Restrict access to confidential supplier contracts | Implemented | Effective | Strategic Sourcing Manager | 2025-07-14 | 2026-08-25 | 2026-11-25
C089 | AI030 | Human Oversight | Procurement professional verifies AI-identified contract risks | Implemented | Effective | Strategic Sourcing Manager | 2025-07-14 | 2026-08-25 | 2026-11-25
C090 | AI030 | Transparency | Require source references for AI-generated contract findings | Partial | Partially Effective | Strategic Sourcing Manager | 2025-10-01 | 2026-08-25 | 2026-10-25
C091 | AI031 | Security | Restrict access to financial forecasting data | Implemented | Effective | Treasury Manager | 2023-03-27 | 2026-05-14 | 2026-11-14
C092 | AI031 | Human Oversight | Treasury analyst approves forecasts used for major decisions | Implemented | Effective | Treasury Manager | 2023-03-27 | 2026-05-14 | 2026-11-14
C093 | AI031 | Reliability | Monthly comparison of forecast versus actual cash flow | Implemented | Effective | Treasury Manager | 2023-04-15 | 2026-08-15 | 2026-11-15
C094 | AI032 | Security | Restrict access to employee expense and audit records | Implemented | Effective | Internal Controls Manager | 2024-05-23 | 2026-07-09 | 2027-01-09
C095 | AI032 | Human Oversight | Auditor reviews all high-risk expense alerts before action | Implemented | Effective | Internal Controls Manager | 2024-05-23 | 2026-07-09 | 2027-01-09
C096 | AI032 | Monitoring | Quarterly review of false-positive expense alerts | Partial | Partially Effective | Internal Controls Manager | 2024-10-01 | 2026-07-09 | 2026-10-09
C097 | AI033 | Fairness | Test credit-risk outcomes for unequal treatment across customer groups | Partial | Partially Effective | Credit Manager | 2024-04-01 | 2026-06-21 | 2026-09-30
C098 | AI033 | Human Oversight | Credit analyst approval required before adverse credit decisions | Implemented | Effective | Credit Manager | 2023-11-13 | 2026-06-21 | 2026-12-21
C099 | AI033 | Transparency | Provide documented reasons supporting adverse credit recommendations | Missing | Not Effective | Credit Manager |  |  | 2026-10-15
C100 | AI034 | Privacy | Automatically redact sensitive customer information from stored summaries | Partial | Partially Effective | Contact Centre Manager | 2025-03-01 | 2026-08-17 | 2026-10-17
C101 | AI034 | Human Oversight | Agent reviews generated call summaries before case closure | Implemented | Effective | Contact Centre Manager | 2025-01-06 | 2026-08-17 | 2026-11-17
C102 | AI034 | Monitoring | Sample generated summaries for omissions and inaccurate statements | Implemented | Effective | Customer Service Quality Manager | 2025-02-15 | 2026-08-17 | 2026-11-17
C103 | AI035 | Fairness | Monitor complaint routing outcomes across customer categories | Partial | Partially Effective | Customer Service Operations Manager | 2025-01-10 | 2026-06-26 | 2026-09-26
C104 | AI035 | Human Oversight | Agents can override complaint routing recommendations | Implemented | Effective | Customer Service Operations Manager | 2024-06-03 | 2026-06-26 | 2026-12-26
C105 | AI035 | Monitoring | Track misrouted complaints and escalation delays | Implemented | Effective | Customer Service Operations Manager | 2024-08-01 | 2026-08-01 | 2026-11-01
C106 | AI036 | Security | Prevent development assistant from accessing unapproved repositories | Implemented | Effective | Software Engineering Manager | 2025-02-24 | 2026-08-06 | 2026-11-06
C107 | AI036 | Human Oversight | Developer review required before AI-generated code is merged | Implemented | Effective | Software Engineering Manager | 2025-02-24 | 2026-08-06 | 2026-11-06
C108 | AI036 | Monitoring | Scan AI-generated code for vulnerabilities and insecure patterns | Partial | Partially Effective | Application Security Manager | 2025-05-01 | 2026-08-06 | 2026-10-06
C109 | AI037 | Security | Continuous monitoring and updating of phishing detection rules | Implemented | Effective | Cybersecurity Operations Manager | 2023-02-16 | 2026-07-28 | 2026-10-28
C110 | AI037 | Human Oversight | Security analyst reviews high-confidence phishing detections | Implemented | Effective | Cybersecurity Operations Manager | 2023-02-16 | 2026-07-28 | 2026-10-28
C111 | AI037 | Monitoring | Track missed phishing emails and false-positive detections | Implemented | Effective | Cybersecurity Manager | 2023-05-01 | 2026-07-28 | 2026-10-28
C112 | AI038 | Privacy | Restrict access to sensitive-data classification results | Implemented | Effective | Data Security Manager | 2024-01-29 | 2026-06-13 | 2026-12-13
C113 | AI038 | Reliability | Quarterly validation of sensitive-data classification accuracy | Implemented | Effective | Data Security Manager | 2024-01-29 | 2026-06-13 | 2026-12-13
C114 | AI038 | Human Oversight | Security staff manually review uncertain classifications | Partial | Partially Effective | Data Security Manager | 2024-06-01 | 2026-06-13 | 2026-09-30
C115 | AI039 | Reliability | Validate calibration predictions against equipment inspection results | Implemented | Effective | Quality Engineering Manager | 2024-04-15 | 2026-07-22 | 2026-10-22
C116 | AI039 | Human Oversight | Technician confirms calibration requirement before equipment adjustment | Implemented | Effective | Quality Engineering Manager | 2024-04-15 | 2026-07-22 | 2026-10-22
C117 | AI039 | Monitoring | Track missed calibration events and unnecessary calibration alerts | Implemented | Effective | Quality Systems Manager | 2024-07-01 | 2026-07-22 | 2026-10-22
C118 | AI040 | Reliability | Quarterly supplier-quality model performance validation | Implemented | Effective | Supplier Quality Manager | 2023-10-02 | 2026-05-31 | 2026-11-30
C119 | AI040 | Human Oversight | Supplier quality engineer reviews high-risk supplier predictions | Implemented | Effective | Supplier Quality Manager | 2023-10-02 | 2026-05-31 | 2026-11-30
C120 | AI040 | Transparency | Document major factors influencing supplier quality risk scores | Partial | Partially Effective | Supplier Quality Manager | 2024-08-01 | 2026-05-31 | 2026-11-30
C121 | AI041 | Reliability | Compare predicted campaign performance with actual results | Implemented | Effective | Marketing Analytics Manager | 2024-03-19 | 2026-06-10 | 2026-12-10
C122 | AI041 | Human Oversight | Marketing analyst reviews predictions before budget allocation | Implemented | Effective | Marketing Analytics Manager | 2024-03-19 | 2026-06-10 | 2026-12-10
C123 | AI041 | Monitoring | Track forecasting error across campaign types | Implemented | Effective | Marketing Analytics Manager | 2024-06-01 | 2026-08-01 | 2026-11-01
C124 | AI042 | Privacy | Limit customer information used by lead-scoring model | Implemented | Effective | Sales Operations Manager | 2023-06-29 | 2026-05-24 | 2026-11-24
C125 | AI042 | Fairness | Review lead scores for inappropriate demographic proxy effects | Partial | Partially Effective | Sales Operations Manager | 2024-09-01 | 2026-05-24 | 2026-11-24
C126 | AI042 | Human Oversight | Sales representatives can override lead priority recommendations | Implemented | Effective | Sales Operations Manager | 2023-06-29 | 2026-05-24 | 2026-11-24
C127 | AI043 | Privacy | Collect only publicly available social media information | Implemented | Effective | Brand Manager | 2024-12-09 | 2026-08-03 | 2027-02-03
C128 | AI043 | Human Oversight | Brand analyst reviews sentiment alerts before escalation | Implemented | Effective | Brand Manager | 2024-12-09 | 2026-08-03 | 2027-02-03
C129 | AI043 | Monitoring | Review incorrect sentiment and topic classifications | Implemented | Effective | Brand Manager | 2025-02-01 | 2026-08-03 | 2026-11-03
C130 | AI044 | Reliability | Validate digital-twin outputs against real production performance | Implemented | Effective | Systems Engineering Manager | 2025-01-13 | 2026-07-16 | 2026-10-16
C131 | AI044 | Human Oversight | Engineer approval required before optimization changes are implemented | Implemented | Effective | Systems Engineering Manager | 2025-01-13 | 2026-07-16 | 2026-10-16
C132 | AI044 | Monitoring | Track simulation error after production-process changes | Implemented | Effective | Systems Engineering Manager | 2025-04-01 | 2026-07-16 | 2026-10-16
C133 | AI045 | Security | Limit AI access to authorized engineering requirement documents | Implemented | Effective | Engineering Program Manager | 2025-04-28 | 2026-08-20 | 2026-11-20
C134 | AI045 | Human Oversight | Engineer verifies AI-generated requirement summaries | Implemented | Effective | Engineering Program Manager | 2025-04-28 | 2026-08-20 | 2026-11-20
C135 | AI045 | Monitoring | Review omitted or incorrectly interpreted technical requirements | Partial | Partially Effective | Engineering Program Manager | 2025-07-15 | 2026-08-20 | 2026-10-20
C136 | AI046 | Privacy | Restrict attrition model access to authorized HR personnel | Implemented | Effective | People Analytics Manager | 2024-08-26 | 2026-06-29 | 2026-12-29
C137 | AI046 | Fairness | Quarterly testing for unequal attrition-risk scores across employee groups | Partial | Partially Effective | People Analytics Manager | 2025-01-15 | 2026-06-29 | 2026-09-29
C138 | AI046 | Transparency | Provide documented explanation of factors influencing employee risk scores | Missing | Not Effective | People Analytics Manager |  |  | 2026-10-10
C139 | AI047 | Privacy | Limit employee profile attributes used for learning recommendations | Implemented | Effective | Learning and Development Manager | 2025-03-17 | 2026-08-11 | 2027-02-11
C140 | AI047 | Fairness | Monitor training recommendations for unequal access to development opportunities | Partial | Partially Effective | Learning and Development Manager | 2025-06-01 | 2026-08-11 | 2026-11-11
C141 | AI047 | Human Oversight | Employees and managers can override training recommendations | Implemented | Effective | Learning and Development Manager | 2025-03-17 | 2026-08-11 | 2027-02-11
C142 | AI048 | Reliability | Routine validation of robot routing performance and collision avoidance | Implemented | Effective | Warehouse Operations Manager | 2024-07-08 | 2026-07-04 | 2026-10-04
C143 | AI048 | Human Oversight | Warehouse operators can immediately stop automated equipment | Implemented | Effective | Warehouse Operations Manager | 2024-07-08 | 2026-07-04 | 2026-10-04
C144 | AI048 | Monitoring | Track routing failures near misses and manual interventions | Implemented | Effective | Warehouse Safety Manager | 2024-08-15 | 2026-07-04 | 2026-10-04
C145 | AI049 | Privacy | Limit retention and access to workplace camera footage | Partial | Partially Effective | EHS Manager | 2026-01-19 | 2026-08-27 | 2026-10-27
C146 | AI049 | Reliability | Validate safety detection accuracy across operating conditions | Implemented | Effective | EHS Manager | 2026-01-19 | 2026-08-27 | 2026-10-27
C147 | AI049 | Human Oversight | Safety professional verifies alerts before corrective action | Implemented | Effective | EHS Manager | 2026-01-19 | 2026-08-27 | 2026-10-27
C148 | AI050 | Security | Restrict assistant access to approved finance records | Implemented | Effective | Financial Reporting Manager | 2026-02-09 | 2026-08-29 | 2026-11-29
C149 | AI050 | Human Oversight | Accountant reviews all AI-generated reconciliation suggestions | Implemented | Effective | Financial Reporting Manager | 2026-02-09 | 2026-08-29 | 2026-11-29
C150 | AI050 | Monitoring | Review incorrect financial close recommendations and hallucinations | Partial | Partially Effective | Financial Reporting Manager | 2026-04-01 | 2026-08-29 | 2026-10-29

## ai_incidents
Incident_ID | AI_System_ID | Incident_Date | Incident_Type | Severity | Description | Business_Impact | Root_Cause_Category | Status | Resolution_Date
INC001 | AI001 | 2026-02-18 | Fairness Complaint | High | Qualified applicants from one candidate group were ranked lower than expected | Potential unequal access to employment opportunities | Training Data Bias | Investigating
INC002 | AI001 | 2026-05-07 | Incorrect Prediction | Medium | Several qualified applicants received unusually low screening scores | Recruiters required manual re-review of applications | Model Drift | Resolved | 2026-05-15
INC003 | AI002 | 2026-03-12 | Fairness Complaint | Medium | Weekend shifts were repeatedly concentrated among a subset of employees | Employee complaints and schedule rework | Optimization Configuration | Resolved | 2026-03-25
INC004 | AI003 | 2026-01-28 | Incorrect Prediction | High | System failed to identify an impending equipment bearing failure | Unplanned production downtime | Sensor Data Quality | Resolved | 2026-02-04
INC005 | AI003 | 2026-06-09 | Model Drift | Medium | Prediction accuracy declined after installation of new equipment sensors | Increase in unnecessary maintenance alerts | Model Drift | Resolved | 2026-06-21
INC006 | AI005 | 2026-04-17 | Incorrect Prediction | Medium | Good products were incorrectly classified as defective | Increased scrap review and production delays | Threshold Calibration | Resolved | 2026-04-23
INC007 | AI005 | 2026-07-11 | Incorrect Prediction | High | Defective products were missed during a production shift | Additional quality inspection and shipment hold | Image Quality | Resolved | 2026-07-13
INC008 | AI007 | 2026-02-22 | Incorrect Prediction | Medium | Low-risk supplier was incorrectly classified as high risk | Supplier review effort increased unnecessarily | Data Quality | Resolved | 2026-03-01
INC009 | AI008 | 2026-03-08 | Incorrect Prediction | Medium | Legitimate invoices were repeatedly flagged as suspicious | Payment delays and additional review workload | Threshold Calibration | Resolved | 2026-03-18
INC010 | AI009 | 2026-01-14 | Hallucination | Medium | Chatbot provided an incorrect warranty policy to a customer | Customer complaint and manual service recovery | Prompt Output Failure | Resolved | 2026-01-15
INC011 | AI009 | 2026-04-26 | Privacy Exposure | High | Chatbot response included information from another customer case | Potential customer privacy breach | Access Control | Remediated | 2026-04-27
INC012 | AI009 | 2026-08-06 | Hallucination | Medium | Chatbot invented a product feature that did not exist | Incorrect customer guidance | Prompt Output Failure | Resolved | 2026-08-07
INC013 | AI010 | 2026-02-10 | Unauthorized Information Exposure | High | Internal assistant displayed confidential project information to an unauthorized employee | Confidentiality risk and internal investigation | Access Control | Remediated | 2026-02-12
INC014 | AI010 | 2026-07-19 | Hallucination | Medium | Assistant generated an incorrect internal policy summary | Employees received misleading procedural guidance | Prompt Output Failure | Resolved | 2026-07-20
INC015 | AI012 | 2026-05-02 | Model Drift | Medium | Customer churn prediction accuracy declined after pricing changes | Retention team targeted incorrect customer segments | Model Drift | Resolved | 2026-05-21
INC016 | AI013 | 2026-03-29 | False Positive | Medium | Normal administrator activity triggered multiple high-risk security alerts | Cybersecurity analyst workload increased | Threshold Calibration | Resolved | 2026-04-05
INC017 | AI014 | 2026-06-14 | Hallucination | Low | Help desk assistant recommended an outdated software troubleshooting procedure | Minor employee productivity loss | Knowledge Base Quality | Resolved | 2026-06-15
INC018 | AI015 | 2026-04-09 | Incorrect Prediction | High | Legitimate administrator access was rated as highly suspicious | Temporary delay in privileged access approval | Model Configuration | Resolved | 2026-04-18
INC019 | AI018 | 2026-03-20 | Hallucination | Medium | Root cause tool suggested an unsupported equipment failure mechanism | Engineering team spent time investigating an unlikely cause | Prompt Output Failure | Resolved | 2026-03-22
INC020 | AI020 | 2026-02-07 | Fairness Concern | Medium | Segmentation model relied heavily on a geographic variable correlated with income | Potential inappropriate customer targeting | Proxy Variable Risk | Investigating
INC021 | AI021 | 2026-06-18 | Fairness Concern | Medium | Recommendation exposure differed substantially across customer groups | Potential unequal product visibility | Recommendation Bias | Open
INC022 | AI022 | 2026-05-04 | Pricing Error | High | Optimization model recommended an unusually large price increase for a product category | Potential revenue and customer trust impact | Data Quality | Resolved | 2026-05-05
INC023 | AI023 | 2026-03-31 | Unsafe Recommendation | High | Design assistant proposed a material unsuitable for operating temperature requirements | Potential engineering safety risk | Prompt Output Failure | Resolved | 2026-04-01
INC024 | AI024 | 2026-07-02 | Incorrect Prediction | Medium | Simulation underestimated equipment energy consumption under peak conditions | Engineering analysis had to be repeated | Model Assumption Error | Resolved | 2026-07-09
INC025 | AI025 | 2026-01-25 | False Negative | High | Drawing review system failed to flag a dimensional inconsistency | Engineering review delay and design rework | Training Data Gap | Resolved | 2026-01-28
INC026 | AI027 | 2026-06-06 | False Negative | High | Safety model failed to flag operating conditions later associated with a minor incident | Safety investigation and model review | Model Drift | Investigating
INC027 | AI030 | 2026-08-02 | Hallucination | High | Contract assistant incorrectly summarized a supplier termination clause | Procurement decision was temporarily delayed | Prompt Output Failure | Resolved | 2026-08-03
INC028 | AI033 | 2026-02-16 | Fairness Complaint | High | Similar credit profiles received different risk classifications | Potential unfair customer credit treatment | Model Bias | Investigating
INC029 | AI033 | 2026-07-07 | Incorrect Prediction | High | Low-risk customer was classified as high credit risk | Credit approval delayed pending manual review | Data Quality | Resolved | 2026-07-11
INC030 | AI034 | 2026-05-18 | Privacy Exposure | High | Generated call summary retained sensitive customer information unnecessarily | Privacy review and data removal required | Data Minimization Failure | Remediated | 2026-05-19
INC031 | AI036 | 2026-04-11 | Security Vulnerability | High | AI-generated code introduced an insecure input validation pattern | Development release delayed for remediation | Unsafe Code Generation | Resolved | 2026-04-13
INC032 | AI037 | 2026-01-19 | False Negative | High | Phishing message was not identified by the detection model | Employee mailbox exposure and security investigation | Model Evasion | Resolved | 2026-01-20
INC033 | AI038 | 2026-06-25 | Incorrect Classification | Medium | Confidential engineering file was classified as normal internal data | Incorrect information protection level applied | Training Data Gap | Resolved | 2026-06-26
INC034 | AI040 | 2026-04-06 | Incorrect Prediction | Medium | Supplier quality model overstated risk for a recently improved supplier | Unnecessary supplier corrective action review | Outdated Data | Resolved | 2026-04-15
INC035 | AI042 | 2026-03-15 | Fairness Concern | Medium | Lead scoring appeared to systematically favor customers from certain regions | Sales allocation required review | Proxy Variable Risk | Open
INC036 | AI045 | 2026-07-26 | Hallucination | High | Requirements assistant omitted an important compliance requirement from its summary | Engineering review had to be repeated | Prompt Output Failure | Resolved | 2026-07-27
INC037 | AI046 | 2026-02-27 | Fairness Concern | High | Attrition model produced substantially different risk distributions between employee groups | Potential inappropriate employee intervention decisions | Model Bias | Investigating
INC038 | AI048 | 2026-05-23 | System Failure | High | Warehouse routing system temporarily stopped responding during peak operations | Warehouse delays and manual routing required | Integration Error | Resolved | 2026-05-23
INC039 | AI049 | 2026-08-08 | False Positive | Medium | Safety vision system repeatedly flagged compliant workers as missing protective equipment | Alert fatigue during pilot testing | Image Quality | Open
INC040 | AI050 | 2026-06-30 | Hallucination | High | Financial close assistant suggested an incorrect reconciliation adjustment | Accountant detected issue before posting | Prompt Output Failure | Resolved | 2026-06-30

## remediation_plan
Remediation_ID | AI_System_ID | System_Name | Governance_Issue | Recommended_Action | Priority | Action_Owner | Start_Date | Target_Date | Status | Dependency | Success_Metric
REM001 | AI033 | Customer Credit Risk Model | Incomplete fairness testing | Implement quarterly fairness testing across customer groups and document outcome disparities | Critical | Credit Manager | 2026-10-01 | 2026-11-15 | Planned | Compliance and Legal Review | Quarterly fairness assessment completed with documented results
REM002 | AI033 | Customer Credit Risk Model | Missing decision transparency | Implement documented reason codes for adverse credit recommendations | Critical | Credit Manager | 2026-10-15 | 2026-12-15 | Planned | Model documentation and IT support | 100% of adverse recommendations include documented reason codes
REM003 | AI001 | Resume Screening Assistant | Incomplete fairness monitoring | Implement quarterly selection-rate and bias testing across candidate groups | Critical | People Analytics Manager | 2026-10-01 | 2026-11-30 | Planned | HR Legal Review | Quarterly fairness testing completed and exceptions investigated
REM004 | AI001 | Resume Screening Assistant | Missing candidate recommendation explanations | Develop documented explanations for AI-assisted candidate recommendations | Critical | Talent Acquisition Manager | 2026-10-15 | 2026-12-15 | Planned | Vendor documentation | 100% of AI recommendations available with reviewable explanation
REM005 | AI015 | Access Risk Analyzer | Incomplete validation of access-risk scoring rules | Complete quarterly validation of access-risk scoring rules and document threshold changes | Critical | Cybersecurity Governance Manager | 2026-10-15 | 2026-12-01 | Planned | Identity and Access data and analyst review | Quarterly validation completed with approved scoring thresholds
REM006 | AI015 | Access Risk Analyzer | False-positive access risk classifications | Recalibrate risk thresholds and test model performance against historical privileged-access cases | Critical | Identity and Access Manager | 2026-11-01 | 2027-01-15 | Planned | Completed scoring-rule validation and historical test data | False-positive rate reduced by at least 25% from baseline during validation
REM007 | AI010 | Internal Knowledge Assistant | Insufficient hallucination monitoring | Implement recurring review of generated responses and hallucination tracking | Critical | IT Applications Manager | 2026-10-01 | 2026-11-15 | Planned | Monitoring workflow and reviewer capacity | Monthly hallucination rate reported and tracked
REM008 | AI010 | Internal Knowledge Assistant | Restricted information exposure risk | Strengthen role-based access controls and test permissions to restricted knowledge sources | Critical | Data Security Manager | 2026-10-01 | 2026-12-01 | Planned | Identity and Access Management support | Zero unauthorized restricted-document access in validation testing
REM009 | AI046 | Employee Attrition Predictor | Incomplete fairness testing | Implement quarterly fairness analysis across employee groups before intervention decisions | Critical | People Analytics Manager | 2026-10-15 | 2026-12-15 | Planned | HR Legal and Privacy Review | All material fairness disparities documented and reviewed
REM010 | AI046 | Employee Attrition Predictor | Insufficient transparency | Create model documentation explaining major factors influencing attrition-risk scores | Critical | People Analytics Manager | 2026-11-01 | 2027-01-31 | Planned | Data Science documentation | 100% of reviewed predictions supported by documented model factors

## project_charter
Project Name | Enterprise AI Governance Remediation Program
Project Objective | Reduce governance risk across NorthStar Manufacturing’s highest-priority AI systems by addressing critical control weaknesses, strengthening oversight, and improving monitoring.
Scope | Top 5 AI systems identified through the Governance Priority Score
Timeline | October 2026 – March 2027
Project Sponsor | Chief Risk Officer
Project Lead | AI Governance Analyst
Key Stakeholders | System Owners, HR, IT, Cybersecurity, Legal, Privacy, Finance, Data/Analytics
Key Deliverables | Remediation plan, fairness testing, access-risk model validation, security/access improvements, transparency documentation, monitoring improvements, control testing
Success Metrics | Increase control coverage toward 90%; eliminate missing priority-system controls; assign accountable owners; complete follow-up assessments

## tbl_project_timeline
Task_ID | Phase | Task | Owner | Start_Date | End_Date | Dependency | Status | Duration_Days | Task | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
T001 | Assessment & Planning | Confirm top 5 priority AI systems | AI Governance Analyst | 2026-10-01 | 2026-10-07 | None | Planned | 7 | Confirm top 5 priority AI systems
T002 | Assessment & Planning | Confirm remediation owners and responsibilities | AI Governance Analyst | 2026-10-01 | 2026-10-10 | T001 | Planned | 10 | Confirm remediation owners and responsibilities
T003 | Assessment & Planning | Review open incidents and control deficiencies | AI Governance Analyst | 2026-10-05 | 2026-10-15 | T001 | Planned | 11 | Review open incidents and control deficiencies
T004 | Control Remediation | Implement fairness testing for credit and employment AI systems | People Analytics and Credit Risk | 2026-10-15 | 2026-11-30 | T003 | Planned | 47 | Implement fairness testing for credit and employment AI systems
T005 | Control Remediation | Develop AI decision transparency documentation | System Owners | 2026-10-15 | 2026-12-15 | T003 | Planned | 62 | Develop AI decision transparency documentation
T006 | Control Remediation | Validate access-risk scoring and reduce false positives | Identity and Access / Cybersecurity | 2026-11-01 | 2027-01-15 | T003 | Planned | 76 | Validate access-risk scoring and reduce false positives
T007 | Control Remediation | Implement generative AI hallucination monitoring | IT Applications Manager | 2026-10-15 | 2026-12-15 | T003 | Planned | 62 | Implement generative AI hallucination monitoring
T008 | Validation & Testing | Test remediated governance controls | AI Governance Analyst | 2027-01-15 | 2027-02-15 | T004,T005,T006,T007 | Planned | 32 | Test remediated governance controls
T009 | Validation & Testing | Perform follow-up AI risk assessments | AI Governance Analyst | 2027-02-01 | 2027-02-28 | T008 | Planned | 28 | Perform follow-up AI risk assessments
T010 | Closeout & Monitoring | Prepare executive governance report | AI Governance Analyst | 2027-03-01 | 2027-03-15 | T009 | Planned | 15 | Prepare executive governance report
T011 | Closeout & Monitoring | Transition priority systems to recurring monitoring | System Owners | 2027-03-15 | 2027-03-31 | T010 | Planned | 17 | Transition priority systems to recurring monitoring

## project_risks
Risk_ID | Project Risk | Likelihood | Impact | Mitigation | Owner | Status
PR001 | AI vendor delays technical documentation | Medium | High | Request documentation early and escalate overdue items | AI Governance Analyst | Open
PR002 | Business teams resist additional governance controls | Medium | High | Involve system owners early and explain business impact of remediation | Project Lead | Open
PR003 | Limited governance resources delay remediation | High | Medium | Prioritize Critical systems and phase lower-priority work | Chief Risk Officer | Open
PR004 | AI models change during remediation work | Medium | High | Require formal change-control review before major model updates | System Owner | Open
PR005 | Incomplete incident documentation affects root-cause analysis | Medium | Medium | Introduce a standardized AI incident reporting template | AI Governance Analyst | Open
PR006 | Privacy or legal review delays control implementation | Medium | High | Schedule Legal and Privacy reviews as early dependencies | Project Lead | Open

## RACI
Activity | AI Governance Analyst | System Owner | IT/Security | Legal/Privacy | Executive Sponsor | Legend | Meaning
Risk Assessment | R | C | C | C | I | R | Responsible
Remediation Planning | R | A | C | C | I | A | Accountable
Control Implementation | C | A/R | R | C | I | C | Consulted
Control Testing | R | C | C | C | I | I | Informed
Incident Review | R | C | R | C | I
Follow-Up Risk Assessment | R | C | C | C | I
Risk Acceptance | C | R | C | C | A
Executive Reporting | R | I | I | I | A
Recurring Monitoring | C | A/R | R | I | I